## Project tasks
Project name | Virtual Jukebox
Project manager | Austin Bevacqua
Project start date | 2022-04-11 09:00
Project finish date | 2022-10-21 17:00
Duration | 125 days
% complete | 0%
Exported on | 2022-05-01 10:54
Task number | Outline number | Name | Start | Finish | Assigned to | Duration | Effort | Depends on | % complete | Bucket | Dependents (after) | Effort completed | Effort remaining | Milestone | Notes | Completed | Checklist Items | Labels
1 | 1 | Package 3 | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days | 181 hours |  | 0% |  |  | 0 hours | 181 hours | No
2 | 1.1 | Solution Specification | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days | 171 hours |  | 0% |  |  | 0 hours | 171 hours | No
3 | 1.1.1 | Business Requirements and Goals | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days | 18 hours |  | 0% |  |  | 0 hours | 18 hours | No
4 | 1.1.1.1 | Business Drivers | 2022-05-02 09:00 | 2022-05-27 17:00 | Ryan Webster | 20 days | 2 hours |  | 0% | Package 3 |  | 0 hours | 2 hours | No
5 | 1.1.1.2 | Solution Requirements | 2022-05-02 09:00 | 2022-05-27 17:00 | Ryan Webster | 20 days | 8 hours |  | 0% | Package 3 |  | 0 hours | 8 hours | No
6 | 1.1.1.3 | High Level Metrics for Success | 2022-05-02 09:00 | 2022-05-06 17:00 | Ryan Webster | 5 days | 3 hours |  | 0% | Package 3 | 36 - Validation of Solution Metrics | 0 hours | 3 hours | No
7 | 1.1.1.4 | Architecture Boundary | 2022-05-02 09:00 | 2022-05-27 17:00 | Ryan Webster | 20 days | 5 hours |  | 0% | Package 3 |  | 0 hours | 5 hours | No
8 | 1.1.2 | Business Model | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days | 22 hours |  | 0% |  |  | 0 hours | 22 hours | No
9 | 1.1.2.1 | Organisational Context | 2022-05-02 09:00 | 2022-05-27 17:00 | Austin Bevacqua | 20 days | 2 hours |  | 0% | Package 3 |  | 0 hours | 2 hours | No
10 | 1.1.2.2 | Current Situtation | 2022-05-02 09:00 | 2022-05-27 17:00 | Austin Bevacqua | 20 days | 3 hours |  | 0% | Package 3 |  | 0 hours | 3 hours | No
11 | 1.1.2.3 | Solution Definition | 2022-05-02 09:00 | 2022-05-27 17:00 | Austin Bevacqua | 20 days | 3 hours |  | 0% | Package 3 |  | 0 hours | 3 hours | No
12 | 1.1.2.4 | Actors | 2022-05-02 09:00 | 2022-05-03 17:00 | Austin Bevacqua | 2 days | 3 hours |  | 0% | Package 3 | 13 - Interactions of Actors | 0 hours | 3 hours | No
13 | 1.1.2.5 | Interactions of Actors | 2022-05-04 09:00 | 2022-05-05 17:00 | Austin Bevacqua | 2 days | 3 hours | 12 - Actors | 0% | Package 3 | 14 - Use Cases | 0 hours | 3 hours | No
14 | 1.1.2.6 | Use Cases | 2022-05-06 09:00 | 2022-05-18 17:00 | Austin Bevacqua | 9 days | 8 hours | 13 - Interactions of Actors | 0% | Package 3 | 35 - Use Case Validation | 0 hours | 8 hours | No
15 | 1.1.3 | Solution Architecture Model | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days | 31 hours |  | 0% |  |  | 0 hours | 31 hours | No
16 | 1.1.3.1 | Solution Components | 2022-05-02 09:00 | 2022-05-27 17:00 | Bradley Vanderzwan | 20 days | 5 hours |  | 0% | Package 3 |  | 0 hours | 5 hours | No
17 | 1.1.3.2 | Integration Specification | 2022-05-02 09:00 | 2022-05-27 17:00 | Bradley Vanderzwan | 20 days | 5 hours |  | 0% | Package 3 |  | 0 hours | 5 hours | No
18 | 1.1.3.3 | Walk-Throughs | 2022-05-02 09:00 | 2022-05-27 17:00 | Bradley Vanderzwan | 20 days | 13 hours |  | 0% | Package 3 |  | 0 hours | 13 hours | No
19 | 1.1.3.4 | Information Model | 2022-05-02 09:00 | 2022-05-27 17:00 | Bradley Vanderzwan | 20 days | 8 hours |  | 0% | Package 3 |  | 0 hours | 8 hours | No
20 | 1.1.4 | Detailed Physical Architecture | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days | 29 hours |  | 0% |  |  | 0 hours | 29 hours | No
21 | 1.1.4.1 | Network Diagram | 2022-05-02 09:00 | 2022-05-27 17:00 | Dillon Vincent | 20 days | 13 hours |  | 0% | Package 3 |  | 0 hours | 13 hours | No
22 | 1.1.4.2 | System Specification Summary | 2022-05-02 09:00 | 2022-05-27 17:00 | Ryan Webster | 20 days | 8 hours |  | 0% | Package 3 |  | 0 hours | 8 hours | No
23 | 1.1.4.3 | Configuration Requirements | 2022-05-02 09:00 | 2022-05-27 17:00 | Ryan Webster | 20 days | 8 hours |  | 0% | Package 3 |  | 0 hours | 8 hours | No
24 | 1.1.5 | Solution Impact | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days | 7 hours |  | 0% |  |  | 0 hours | 7 hours | No
25 | 1.1.5.1 | Impact on Processes | 2022-05-02 09:00 | 2022-05-27 17:00 | Dillon Vincent | 20 days | 2 hours |  | 0% | Package 3 |  | 0 hours | 2 hours | No
26 | 1.1.5.2 | Impact on People | 2022-05-02 09:00 | 2022-05-27 17:00 | Dillon Vincent | 20 days | 2 hours |  | 0% | Package 3 |  | 0 hours | 2 hours | No
27 | 1.1.5.3 | Technical Impact | 2022-05-02 09:00 | 2022-05-27 17:00 | Dillon Vincent | 20 days | 3 hours |  | 0% | Package 3 |  | 0 hours | 3 hours | No
28 | 1.1.6 | Quality Attributes | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days | 19 hours |  | 0% |  |  | 0 hours | 19 hours | No
29 | 1.1.6.1 | Reliability | 2022-05-02 09:00 | 2022-05-27 17:00 | Tanaka Chitete | 20 days | 3 hours |  | 0% | Package 3 |  | 0 hours | 3 hours | No
30 | 1.1.6.2 | Availability | 2022-05-02 09:00 | 2022-05-27 17:00 | Tanaka Chitete | 20 days | 3 hours |  | 0% | Package 3 |  | 0 hours | 3 hours | No
31 | 1.1.6.3 | Serviceability | 2022-05-02 09:00 | 2022-05-27 17:00 | Tanaka Chitete | 20 days | 3 hours |  | 0% | Package 3 |  | 0 hours | 3 hours | No
32 | 1.1.6.4 | Best Practice Commentary | 2022-05-02 09:00 | 2022-05-27 17:00 | Tanaka Chitete | 20 days | 5 hours |  | 0% | Package 3 |  | 0 hours | 5 hours | No
33 | 1.1.6.5 | Architecture Commentary | 2022-05-02 09:00 | 2022-05-27 17:00 | Tanaka Chitete | 20 days | 5 hours |  | 0% | Package 3 |  | 0 hours | 5 hours | No
34 | 1.1.7 | Success Criteria and Test Plan | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days | 13 hours |  | 0% |  |  | 0 hours | 13 hours | No
35 | 1.1.7.1 | Use Case Validation | 2022-05-19 09:00 | 2022-05-27 17:00 | Dillon Vincent | 7 days | 3 hours | 14 - Use Cases | 0% | Package 3 |  | 0 hours | 3 hours | No
36 | 1.1.7.2 | Validation of Solution Metrics | 2022-05-19 09:00 | 2022-05-27 17:00 | Dillon Vincent | 7 days | 5 hours | 6 - High Level Metrics for Success | 0% | Package 3 |  | 0 hours | 5 hours | No
37 | 1.1.7.3 | Test Plan | 2022-05-02 09:00 | 2022-05-27 17:00 | Dillon Vincent | 20 days | 5 hours |  | 0% | Package 3 |  | 0 hours | 5 hours | No
38 | 1.1.8 | Phasing, Roadmap, and Implementation Plan | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days | 11 hours |  | 0% |  |  | 0 hours | 11 hours | No
39 | 1.1.8.1 | Technical Assumptions | 2022-05-02 09:00 | 2022-05-27 17:00 | Tanaka Chitete | 20 days | 2 hours |  | 0% | Package 3 |  | 0 hours | 2 hours | No
40 | 1.1.8.2 | Solution Phases and Technical Milestones | 2022-05-02 09:00 | 2022-05-27 17:00 | Tanaka Chitete | 20 days | 3 hours |  | 0% | Package 3 |  | 0 hours | 3 hours | No
41 | 1.1.8.3 | Technical Work Breakdown Structure | 2022-05-02 09:00 | 2022-05-27 17:00 | Tanaka Chitete | 20 days | 3 hours |  | 0% | Package 3 |  | 0 hours | 3 hours | No
42 | 1.1.8.4 | Implementation Instructions | 2022-05-02 09:00 | 2022-05-27 17:00 | Tanaka Chitete | 20 days | 3 hours |  | 0% | Package 3 |  | 0 hours | 3 hours | No
43 | 1.1.9 | Report Formatting/Editing | 2022-05-23 09:00 | 2022-05-27 17:00 | Dillon Vincent, Bradley Vanderzwan, Tanaka Chitete, Austin Bevacqua, Ryan Webster | 5 days | 21 hours |  | 0% | Package 3 |  | 0 hours | 21 hours | No
44 | 1.2 | Progress Report 3 | 2022-05-23 09:00 | 2022-05-27 17:00 | Austin Bevacqua, Bradley Vanderzwan, Dillon Vincent, Tanaka Chitete, Ryan Webster | 5 days | 8 hours |  | 0% | Package 3 |  | 0 hours | 8 hours | No
45 | 1.3 | Package Submission | 2022-05-27 09:00 | 2022-05-27 17:00 | Bradley Vanderzwan | 1 day | 2 hours |  | 0% | Package 3 |  | 0 hours | 2 hours | No
46 | 2 | Package 4 | 2022-07-25 09:00 | 2022-08-19 17:00 |  | 20 days | 222 hours |  | 0% |  |  | 0 hours | 222 hours | No
47 | 2.1 | Application - 1st release | 2022-07-25 09:00 | 2022-08-19 17:00 |  | 20 days | 217 hours |  | 0% |  |  | 0 hours | 217 hours | No
48 | 2.1.1 | Development Phase | 2022-07-25 09:00 | 2022-08-15 17:00 |  | 16 days | 151 hours |  | 0% |  | 87 - Deployment Phase | 0 hours | 151 hours | No
49 | 2.1.1.1 | Database Implementation | 2022-07-25 09:00 | 2022-08-15 17:00 |  | 16 days | 29 hours |  | 0% |  |  | 0 hours | 29 hours | No
50 | 2.1.1.1.1 | Database Creation | 2022-07-25 09:00 | 2022-07-29 17:00 | Bradley Vanderzwan | 5 days | 13 hours |  | 0% | Package 4 | 52 - Database Hardening and Optimisation, 51 - Database Django ORM Integration | 0 hours | 13 hours | No
51 | 2.1.1.1.2 | Database Django ORM Integration | 2022-08-01 09:00 | 2022-08-03 17:00 | Bradley Vanderzwan | 3 days | 8 hours | 50 - Database Creation | 0% | Package 4 | 62 - Virtual Jukebox Session Settings/Setup Functionality, 58 - Virtual Jukebox User Registration Validation, 55 - Virtual Jukebox User Login Validation, 74 - Virtual Jukebox Session Join Page Validation | 0 hours | 8 hours | No
52 | 2.1.1.1.3 | Database Hardening and Optimisation | 2022-08-03 09:00 | 2022-08-15 17:00 | Bradley Vanderzwan | 9 days | 8 hours | 50 - Database Creation | 0% | Package 4 |  | 0 hours | 8 hours | No
53 | 2.1.1.2 | Virtual Jukebox Account Implementation | 2022-07-25 09:00 | 2022-08-15 17:00 |  | 16 days | 37 hours |  | 0% |  |  | 0 hours | 37 hours | No
54 | 2.1.1.2.1 | Login Implementation | 2022-07-25 09:00 | 2022-08-15 17:00 |  | 16 days | 16 hours |  | 0% |  |  | 0 hours | 16 hours | No
55 | 2.1.1.2.1.1 | Virtual Jukebox User Login Validation | 2022-08-04 09:00 | 2022-08-15 17:00 | Dillon Vincent | 8 days | 8 hours | 51 - Database Django ORM Integration | 0% | Package 4 |  | 0 hours | 8 hours | No
56 | 2.1.1.2.1.2 | Virtual Jukebox User Login Page GUI | 2022-07-25 09:00 | 2022-08-15 17:00 | Tanaka Chitete | 16 days | 8 hours |  | 0% | Package 4 |  | 0 hours | 8 hours | No
57 | 2.1.1.2.2 | Registration Implementation | 2022-07-25 09:00 | 2022-08-15 17:00 |  | 16 days | 21 hours |  | 0% |  |  | 0 hours | 21 hours | No
58 | 2.1.1.2.2.1 | Virtual Jukebox User Registration Validation | 2022-08-04 09:00 | 2022-08-15 17:00 | Dillon Vincent | 8 days | 13 hours | 51 - Database Django ORM Integration | 0% | Package 4 |  | 0 hours | 13 hours | No
59 | 2.1.1.2.2.2 | Virtual Jukebox User Registration Page GUI | 2022-07-25 09:00 | 2022-08-15 17:00 | Tanaka Chitete | 16 days | 8 hours |  | 0% | Package 4 |  | 0 hours | 8 hours | No
60 | 2.1.1.3 | Virtual Jukebox Session Implementation | 2022-07-25 09:00 | 2022-08-15 17:00 |  | 16 days | 85 hours |  | 0% |  |  | 0 hours | 85 hours | No
61 | 2.1.1.3.1 | Host User Implementation | 2022-07-25 09:00 | 2022-08-15 17:00 |  | 16 days | 29 hours |  | 0% |  |  | 0 hours | 29 hours | No
62 | 2.1.1.3.1.1 | Virtual Jukebox Session Settings/Setup Functionality | 2022-08-04 09:00 | 2022-08-15 17:00 | Austin Bevacqua | 8 days | 8 hours | 51 - Database Django ORM Integration | 0% | Package 4 |  | 0 hours | 8 hours | No
63 | 2.1.1.3.1.2 | Virtual Jukebox Session Settings/Setup Page GUI | 2022-07-25 09:00 | 2022-08-15 17:00 | Tanaka Chitete | 16 days | 5 hours |  | 0% | Package 4 |  | 0 hours | 5 hours | No
64 | 2.1.1.3.1.3 | Virtual Jukebox Session Playback Controls | 2022-07-25 09:00 | 2022-08-15 17:00 | Austin Bevacqua | 16 days | 3 hours |  | 0% | Package 4 |  | 0 hours | 3 hours | No
65 | 2.1.1.3.1.4 | Playlist Selection Page GUI | 2022-07-25 09:00 | 2022-08-15 17:00 | Tanaka Chitete | 16 days | 8 hours |  | 0% | Package 4 |  | 0 hours | 8 hours | No
66 | 2.1.1.3.1.5 | Playlist Selection Functionality (via Spotify SDK) | 2022-07-25 09:00 | 2022-08-15 17:00 | Austin Bevacqua | 16 days | 5 hours |  | 0% | Package 4 |  | 0 hours | 5 hours | No
67 | 2.1.1.3.2 | Song Queue Implementation | 2022-07-25 09:00 | 2022-08-15 17:00 |  | 16 days | 30 hours |  | 0% |  |  | 0 hours | 30 hours | No
68 | 2.1.1.3.2.1 | Voting System | 2022-07-25 09:00 | 2022-08-15 17:00 | Ryan Webster | 16 days | 13 hours |  | 0% | Package 4 |  | 0 hours | 13 hours | No
69 | 2.1.1.3.2.2 | Song Queuing Logic | 2022-07-25 09:00 | 2022-08-15 17:00 | Ryan Webster | 16 days | 5 hours |  | 0% | Package 4 |  | 0 hours | 5 hours | No
70 | 2.1.1.3.2.3 | Spotify SDK Integration | 2022-07-25 09:00 | 2022-08-15 17:00 | Ryan Webster | 16 days | 2 hours |  | 0% | Package 4 |  | 0 hours | 2 hours | No
71 | 2.1.1.3.2.4 | Song Selection System | 2022-07-25 09:00 | 2022-08-15 17:00 | Ryan Webster | 16 days | 2 hours |  | 0% | Package 4 |  | 0 hours | 2 hours | No
72 | 2.1.1.3.2.5 | Song Queue GUI | 2022-07-25 09:00 | 2022-08-15 17:00 | Tanaka Chitete | 16 days | 8 hours |  | 0% | Package 4 |  | 0 hours | 8 hours | No
73 | 2.1.1.3.3 | Virtual Jukebox Session Join Page Implementation | 2022-07-25 09:00 | 2022-08-15 17:00 |  | 16 days | 18 hours |  | 0% |  |  | 0 hours | 18 hours | No
74 | 2.1.1.3.3.1 | Virtual Jukebox Session Join Page Validation | 2022-08-04 09:00 | 2022-08-15 17:00 | Dillon Vincent | 8 days | 13 hours | 51 - Database Django ORM Integration | 0% | Package 4 |  | 0 hours | 13 hours | No
75 | 2.1.1.3.3.2 | Virtual Jukebox Session Join Page GUI | 2022-07-25 09:00 | 2022-08-15 17:00 | Tanaka Chitete | 16 days | 5 hours |  | 0% | Package 4 |  | 0 hours | 5 hours | No
76 | 2.1.1.3.4 | Virtual Jukebox Session Active Page Implementation | 2022-07-25 09:00 | 2022-08-15 17:00 |  | 16 days | 8 hours |  | 0% |  |  | 0 hours | 8 hours | No
77 | 2.1.1.3.4.1 | Virtual Jukebox Session Active Page GUI | 2022-07-25 09:00 | 2022-08-15 17:00 | Tanaka Chitete | 16 days | 8 hours |  | 0% | Package 4 |  | 0 hours | 8 hours | No
78 | 2.1.2 | Testing Phase | 2022-08-11 09:00 | 2022-08-15 17:00 |  | 3 days | 32 hours |  | 0% |  |  | 0 hours | 32 hours | No
79 | 2.1.2.1 | Performance Testing | 2022-08-11 09:00 | 2022-08-15 17:00 | Bradley Vanderzwan | 3 days | 8 hours |  | 0% | Package 4 |  | 0 hours | 8 hours | No
80 | 2.1.2.2 | Reliability Testing | 2022-08-11 09:00 | 2022-08-15 17:00 | Bradley Vanderzwan | 3 days | 8 hours |  | 0% | Package 4 |  | 0 hours | 8 hours | No
81 | 2.1.2.3 | Usability Testing | 2022-08-11 09:00 | 2022-08-15 17:00 | Austin Bevacqua | 3 days | 8 hours |  | 0% | Package 4 |  | 0 hours | 8 hours | No
82 | 2.1.2.4 | Security Testing | 2022-08-11 09:00 | 2022-08-15 17:00 | Dillon Vincent | 3 days | 3 hours |  | 0% | Package 4 |  | 0 hours | 3 hours | No
83 | 2.1.2.5 | User Acceptance Testing | 2022-08-11 09:00 | 2022-08-15 17:00 | Austin Bevacqua | 3 days | 5 hours |  | 0% | Package 4 |  | 0 hours | 5 hours | No
84 | 2.1.3 | Remediation Phase | 2022-08-12 09:00 | 2022-08-15 17:00 |  | 2 days | 21 hours |  | 0% |  |  | 0 hours | 21 hours | No
85 | 2.1.3.1 | Bug Fixing | 2022-08-12 09:00 | 2022-08-15 17:00 | Austin Bevacqua, Ryan Webster, Bradley Vanderzwan, Dillon Vincent, Tanaka Chitete | 2 days | 13 hours |  | 0% | Package 4 |  | 0 hours | 13 hours | No
86 | 2.1.3.2 | User Feedback Implementation | 2022-08-12 09:00 | 2022-08-15 17:00 | Austin Bevacqua, Ryan Webster, Bradley Vanderzwan, Dillon Vincent, Tanaka Chitete | 2 days | 8 hours |  | 0% | Package 4 |  | 0 hours | 8 hours | No
87 | 2.1.4 | Deployment Phase | 2022-08-16 09:00 | 2022-08-19 17:00 | Austin Bevacqua, Dillon Vincent | 4 days | 13 hours | 48 - Development Phase | 0% | Package 4 |  | 0 hours | 13 hours | No
88 | 2.2 | Progress Report 4 | 2022-08-15 09:00 | 2022-08-19 17:00 | Austin Bevacqua, Bradley Vanderzwan, Dillon Vincent, Tanaka Chitete, Ryan Webster | 5 days | 5 hours |  | 0% | Package 4 |  | 0 hours | 5 hours | No
89 | 3 | Package 5 | 2022-08-22 09:00 | 2022-09-23 17:00 |  | 25 days | 196 hours |  | 0% |  |  | 0 hours | 196 hours | No
90 | 3.1 | Application - 2nd release | 2022-08-22 09:00 | 2022-09-23 17:00 |  | 25 days | 191 hours |  | 0% |  |  | 0 hours | 191 hours | No
91 | 3.1.1 | Development Phase | 2022-08-22 09:00 | 2022-09-19 17:00 |  | 21 days | 89 hours |  | 0% |  | 113 - Deployment Phase | 0 hours | 89 hours | No
92 | 3.1.1.1 | Virtual Jukebox Session Implementation | 2022-08-22 09:00 | 2022-09-19 17:00 |  | 21 days | 76 hours |  | 0% |  |  | 0 hours | 76 hours | No
93 | 3.1.1.1.1 | Host User Implementation | 2022-08-22 09:00 | 2022-09-19 17:00 |  | 21 days | 21 hours |  | 0% |  |  | 0 hours | 21 hours | No
94 | 3.1.1.1.1.1 | Virtual Jukebox Session Location Setting Functionality | 2022-08-22 09:00 | 2022-09-05 17:00 | Ryan Webster | 11 days | 13 hours |  | 0% | Package 5 | 98 - Virtual Jukebox Session Join Radius Validation | 0 hours | 13 hours | No
95 | 3.1.1.1.1.2 | Virtual Jukebox Session Location Setting GUI | 2022-08-22 09:00 | 2022-09-19 17:00 | Tanaka Chitete | 21 days | 8 hours |  | 0% | Package 5 |  | 0 hours | 8 hours | No
96 | 3.1.1.1.2 | Virtual Jukebox Session Join Page Implementation | 2022-08-22 09:00 | 2022-09-19 17:00 |  | 21 days | 55 hours |  | 0% |  |  | 0 hours | 55 hours | No
97 | 3.1.1.1.2.1 | Virtual Jukebox Map System Implementation | 2022-08-22 09:00 | 2022-09-19 17:00 |  | 21 days | 55 hours |  | 0% |  |  | 0 hours | 55 hours | No
98 | 3.1.1.1.2.1.1 | Virtual Jukebox Session Join Radius Validation | 2022-09-06 09:00 | 2022-09-19 17:00 | Dillon Vincent | 10 days | 13 hours | 94 - Virtual Jukebox Session Location Setting Functionality | 0% | Package 5 |  | 0 hours | 13 hours | No
99 | 3.1.1.1.2.1.2 | Virtual Jukebox Session Active Map Functionality (Mapworks Integration) | 2022-08-22 09:00 | 2022-09-19 17:00 | Austin Bevacqua | 21 days | 21 hours |  | 0% | Package 5 |  | 0 hours | 21 hours | No
100 | 3.1.1.1.2.1.3 | Virtual Jukebox Session Active Map GUI | 2022-08-22 09:00 | 2022-09-19 17:00 | Tanaka Chitete | 21 days | 21 hours |  | 0% | Package 5 |  | 0 hours | 21 hours | No
101 | 3.1.1.2 | Caching Implementation | 2022-08-22 09:00 | 2022-09-19 17:00 |  | 21 days | 13 hours |  | 0% |  |  | 0 hours | 13 hours | No
102 | 3.1.1.2.1 | Playlist Caching | 2022-08-22 09:00 | 2022-09-19 17:00 | Bradley Vanderzwan | 21 days | 5 hours |  | 0% | Package 5 |  | 0 hours | 5 hours | No
103 | 3.1.1.2.2 | Song Queue Caching | 2022-08-22 09:00 | 2022-09-19 17:00 | Bradley Vanderzwan | 21 days | 8 hours |  | 0% | Package 5 |  | 0 hours | 8 hours | No
104 | 3.1.2 | Testing Phase | 2022-09-15 09:00 | 2022-09-19 17:00 |  | 3 days | 55 hours |  | 0% |  |  | 0 hours | 55 hours | No
105 | 3.1.2.1 | Performance Testing | 2022-09-15 09:00 | 2022-09-19 17:00 | Bradley Vanderzwan | 3 days | 13 hours |  | 0% | Package 5 |  | 0 hours | 13 hours | No
106 | 3.1.2.2 | Reliability Testing | 2022-09-15 09:00 | 2022-09-19 17:00 | Bradley Vanderzwan | 3 days | 8 hours |  | 0% | Package 5 |  | 0 hours | 8 hours | No
107 | 3.1.2.3 | Usability Testing | 2022-09-15 09:00 | 2022-09-19 17:00 | Austin Bevacqua | 3 days | 13 hours |  | 0% | Package 5 |  | 0 hours | 13 hours | No
108 | 3.1.2.4 | Security Testing | 2022-09-15 09:00 | 2022-09-19 17:00 | Dillon Vincent | 3 days | 8 hours |  | 0% | Package 5 |  | 0 hours | 8 hours | No
109 | 3.1.2.5 | User Acceptance Testing | 2022-09-15 09:00 | 2022-09-19 17:00 | Austin Bevacqua | 3 days | 13 hours |  | 0% | Package 5 |  | 0 hours | 13 hours | No
110 | 3.1.3 | Remediation Phase | 2022-09-16 09:00 | 2022-09-19 17:00 |  | 2 days | 34 hours |  | 0% |  |  | 0 hours | 34 hours | No
111 | 3.1.3.1 | Bug Fixing | 2022-09-16 09:00 | 2022-09-19 17:00 | Bradley Vanderzwan, Ryan Webster, Dillon Vincent, Austin Bevacqua, Tanaka Chitete | 2 days | 21 hours |  | 0% | Package 5 |  | 0 hours | 21 hours | No
112 | 3.1.3.2 | User Feedback Implementation | 2022-09-16 09:00 | 2022-09-19 17:00 | Bradley Vanderzwan, Ryan Webster, Dillon Vincent, Austin Bevacqua, Tanaka Chitete | 2 days | 13 hours |  | 0% | Package 5 |  | 0 hours | 13 hours | No
113 | 3.1.4 | Deployment Phase | 2022-09-20 09:00 | 2022-09-23 17:00 | Austin Bevacqua, Dillon Vincent | 4 days | 13 hours | 91 - Development Phase | 0% | Package 5 |  | 0 hours | 13 hours | No
114 | 3.2 | Progress Report 5 | 2022-09-19 09:00 | 2022-09-23 17:00 | Austin Bevacqua, Bradley Vanderzwan, Dillon Vincent, Tanaka Chitete, Ryan Webster | 5 days | 5 hours |  | 0% | Package 5 |  | 0 hours | 5 hours | No
115 | 4 | Package 6 | 2022-09-26 09:00 | 2022-10-21 17:00 |  | 20 days | 191 hours |  | 0% |  |  | 0 hours | 191 hours | No
116 | 4.1 | Application - 3rd (final) release | 2022-09-26 09:00 | 2022-10-21 17:00 |  | 20 days | 165 hours |  | 0% |  |  | 0 hours | 165 hours | No
117 | 4.1.1 | Development Phase | 2022-09-26 09:00 | 2022-10-17 17:00 |  | 16 days | 29 hours |  | 0% |  | 133 - Deployment Phase | 0 hours | 29 hours | No
118 | 4.1.1.1 | Virtual Jukebox Session Implementation | 2022-09-26 09:00 | 2022-10-17 17:00 |  | 16 days | 29 hours |  | 0% |  |  | 0 hours | 29 hours | No
119 | 4.1.1.1.1 | Chat Room Implementation | 2022-09-26 09:00 | 2022-10-17 17:00 |  | 16 days | 29 hours |  | 0% |  |  | 0 hours | 29 hours | No
120 | 4.1.1.1.1.1 | Messaging System | 2022-09-26 09:00 | 2022-10-07 17:00 | Ryan Webster | 10 days | 13 hours |  | 0% | Package 6 | 122 - Message Limiting Functionality, 121 - Message Filtering System | 0 hours | 13 hours | No
121 | 4.1.1.1.1.2 | Message Filtering System | 2022-10-10 09:00 | 2022-10-17 17:00 | Ryan Webster | 6 days | 3 hours | 120 - Messaging System | 0% | Package 6 |  | 0 hours | 3 hours | No
122 | 4.1.1.1.1.3 | Message Limiting Functionality | 2022-10-10 09:00 | 2022-10-17 17:00 | Ryan Webster | 6 days | 5 hours | 120 - Messaging System | 0% | Package 6 |  | 0 hours | 5 hours | No
123 | 4.1.1.1.1.4 | Chat Room GUI | 2022-09-26 09:00 | 2022-10-17 17:00 | Tanaka Chitete | 16 days | 8 hours |  | 0% | Package 6 |  | 0 hours | 8 hours | No
124 | 4.1.2 | Testing Phase | 2022-10-13 09:00 | 2022-10-17 17:00 |  | 3 days | 89 hours |  | 0% |  |  | 0 hours | 89 hours | No
125 | 4.1.2.1 | Performance Testing | 2022-10-13 09:00 | 2022-10-17 17:00 | Bradley Vanderzwan, Tanaka Chitete | 3 days | 21 hours |  | 0% | Package 6 |  | 0 hours | 21 hours | No
126 | 4.1.2.2 | Reliability Testing | 2022-10-13 09:00 | 2022-10-17 17:00 | Bradley Vanderzwan, Tanaka Chitete | 3 days | 21 hours |  | 0% | Package 6 |  | 0 hours | 21 hours | No
127 | 4.1.2.3 | Usability Testing | 2022-10-13 09:00 | 2022-10-17 17:00 | Austin Bevacqua, Ryan Webster | 3 days | 21 hours |  | 0% | Package 6 |  | 0 hours | 21 hours | No
128 | 4.1.2.4 | Security Testing | 2022-10-13 09:00 | 2022-10-17 17:00 | Dillon Vincent | 3 days | 13 hours |  | 0% | Package 6 |  | 0 hours | 13 hours | No
129 | 4.1.2.5 | User Acceptance Testing | 2022-10-13 09:00 | 2022-10-17 17:00 | Austin Bevacqua, Ryan Webster | 3 days | 13 hours |  | 0% | Package 6 |  | 0 hours | 13 hours | No
130 | 4.1.3 | Remediation Phase | 2022-10-14 09:00 | 2022-10-17 17:00 |  | 2 days | 34 hours |  | 0% |  |  | 0 hours | 34 hours | No
131 | 4.1.3.1 | Bug Fixing | 2022-10-14 09:00 | 2022-10-17 17:00 | Bradley Vanderzwan, Tanaka Chitete, Austin Bevacqua, Dillon Vincent, Ryan Webster | 2 days | 21 hours |  | 0% | Package 6 |  | 0 hours | 21 hours | No
132 | 4.1.3.2 | User Feedback Implementation | 2022-10-14 09:00 | 2022-10-17 17:00 | Bradley Vanderzwan, Tanaka Chitete, Austin Bevacqua, Dillon Vincent, Ryan Webster | 2 days | 13 hours |  | 0% | Package 6 |  | 0 hours | 13 hours | No
133 | 4.1.4 | Deployment Phase | 2022-10-18 09:00 | 2022-10-21 17:00 | Austin Bevacqua, Dillon Vincent | 4 days | 13 hours | 117 - Development Phase | 0% | Package 6 |  | 0 hours | 13 hours | No
134 | 4.2 | Post-implementation Evaluation | 2022-10-12 09:00 | 2022-10-21 17:00 | Bradley Vanderzwan, Tanaka Chitete, Ryan Webster, Austin Bevacqua, Dillon Vincent | 8 days | 21 hours |  | 0% | Package 6 |  | 0 hours | 21 hours | No
135 | 4.3 | Progress Report 6 (closure report) | 2022-10-17 09:00 | 2022-10-21 17:00 | Austin Bevacqua, Bradley Vanderzwan, Dillon Vincent, Tanaka Chitete, Ryan Webster | 5 days | 5 hours |  | 0% | Package 6 |  | 0 hours | 5 hours | No