## Project tasks
Project name | Virtual Jukebox
Project manager | John Ho
Project start date | 2022-04-11 09:00
Project finish date | 2022-10-21 17:00
Duration | 125 days
% complete | 0%
Exported on | 2022-04-28 12:50
Task number | Outline number | Name | Start | Finish | Assigned to | Duration | Effort | Depends on | % complete | Bucket | Dependents (after) | Effort completed | Effort remaining | Milestone | Notes | Completed | Checklist Items | Labels
1 | 1 | Package 3 | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days |  |  | 0% |  |  |  |  | No
2 | 1.1 | Solution Specification | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days |  |  | 0% |  |  |  |  | No
3 | 1.1.1 | Test Plans | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days |  |  | 0% | Bucket 1 |  |  |  | No
4 | 1.1.2 | Component Descriptions | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days |  |  | 0% | Bucket 1 |  |  |  | No
5 | 1.1.3 | Walkthroughs | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days |  |  | 0% | Bucket 1 |  |  |  | No
6 | 1.1.4 | Architecture Diagrams | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days |  |  | 0% | Bucket 1 |  |  |  | No
7 | 1.1.5 | Use Cases | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days |  |  | 0% | Bucket 1 |  |  |  | No
8 | 1.1.6 | ER Diagram | 2022-05-02 09:00 | 2022-05-27 17:00 |  | 20 days |  |  | 0% | Bucket 1 |  |  |  | No
9 | 1.2 | Progress Report 3 | 2022-05-23 09:00 | 2022-05-27 17:00 |  | 5 days |  |  | 0% | Bucket 1 |  |  |  | No
10 | 2 | Package 4 | 2022-07-25 09:00 | 2022-08-19 17:00 |  | 20 days |  |  | 0% |  |  |  |  | No
11 | 2.1 | Application - 1st release | 2022-07-25 09:00 | 2022-08-19 17:00 |  | 20 days |  |  | 0% |  |  |  |  | No
12 | 2.1.1 | Back-end implementation | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% |  | 30 - Deployment |  |  | No
13 | 2.1.1.1 | Database | 2022-07-25 09:00 | 2022-08-08 17:00 |  | 11 days |  |  | 0% | Bucket 1 | 15 - User login validation, 19 - Caching, 16 - Session join validation |  |  | No
14 | 2.1.1.2 | Song queue logic | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% | Bucket 1 |  |  |  | No
15 | 2.1.1.3 | User login validation | 2022-08-09 09:00 | 2022-08-12 17:00 |  | 4 days |  | 13 - Database | 0% | Bucket 1 |  |  |  | No
16 | 2.1.1.4 | Session join validation | 2022-08-09 09:00 | 2022-08-12 17:00 |  | 4 days |  | 13 - Database | 0% | Bucket 1 |  |  |  | No
17 | 2.1.1.5 | Chat room logic | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% | Bucket 1 |  |  |  | No
18 | 2.1.1.6 | Mapping system logic | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% | Bucket 1 |  |  |  | No
19 | 2.1.1.7 | Caching | 2022-08-09 09:00 | 2022-08-12 17:00 |  | 4 days |  | 13 - Database | 0% | Bucket 1 |  |  |  | No
20 | 2.1.2 | Front-end implementation | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% |  | 30 - Deployment |  |  | No
21 | 2.1.2.1 | Music playback via Spotify | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% | Bucket 1 |  |  |  | No
22 | 2.1.2.2 | Virtual Jukebox GUI | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% |  |  |  |  | No
23 | 2.1.2.2.1 | User login GUI | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% | Bucket 1 |  |  |  | No
24 | 2.1.2.2.2 | Mapping system GUI | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% | Bucket 1 |  |  |  | No
25 | 2.1.2.2.3 | Session GUI | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% |  |  |  |  | No
26 | 2.1.2.2.3.1 | Session join view | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% | Bucket 1 |  |  |  | No
27 | 2.1.2.2.3.2 | Chat room view | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% | Bucket 1 |  |  |  | No
28 | 2.1.2.2.3.3 | Song queue view | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% | Bucket 1 |  |  |  | No
29 | 2.1.2.2.3.4 | Playlist view | 2022-07-25 09:00 | 2022-08-12 17:00 |  | 15 days |  |  | 0% | Bucket 1 |  |  |  | No
30 | 2.1.3 | Deployment | 2022-08-15 09:00 | 2022-08-19 17:00 |  | 5 days |  | 12 - Back-end implementation, 20 - Front-end implementation | 0% | Bucket 1 |  |  |  | No
31 | 2.2 | Progress Report 4 | 2022-08-15 09:00 | 2022-08-19 17:00 |  | 5 days |  |  | 0% | Bucket 1 |  |  |  | No
32 | 3 | Package 5 | 2022-08-22 09:00 | 2022-09-23 17:00 |  | 25 days |  |  | 0% |  |  |  |  | No
33 | 3.1 | Application - 2nd release | 2022-08-22 09:00 | 2022-09-23 17:00 |  | 25 days |  |  | 0% | Bucket 1 |  |  |  | No
34 | 3.2 | Progress Report 5 | 2022-09-19 09:00 | 2022-09-23 17:00 |  | 5 days |  |  | 0% | Bucket 1 |  |  |  | No
35 | 4 | Package 6 | 2022-09-26 09:00 | 2022-10-21 17:00 |  | 20 days |  |  | 0% |  |  |  |  | No
36 | 4.1 | Application - 3rd (final) release | 2022-09-26 09:00 | 2022-10-21 17:00 |  | 20 days |  |  | 0% | Bucket 1 |  |  |  | No
37 | 4.2 | Post-implementation Evaluation | 2022-10-12 09:00 | 2022-10-21 17:00 |  | 8 days |  |  | 0% | Bucket 1 |  |  |  | No
38 | 4.3 | Progress Report (6 - closure report) | 2022-10-17 09:00 | 2022-10-21 17:00 |  | 5 days |  |  | 0% | Bucket 1 |  |  |  | No